## 2021F - Project Dashboard
2021F - Project Dashboard

## Timesheet Data
Id | Title | DeliverableId | Project PhaseId | TaskId | Hours | Task Date | Start of Week | End of Task | Author.Title | Editor.Title | Deliverable.Title | Project Phase.Title | Task.Title | Task.Budgeted Hours | Assigned To.Title | Weekely Budgeted Hours | Cost
1 | Timesheet 2021-12-10 | 1 | 1 | 23 | 1 | 2021-12-10 | 2021-12-05 | 2021-12-10 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Client Acceptance of the project charter | 1 | Deepkumar Patel | 12 | 50
2 | Timesheet 2022-01-02 | 1 | 1 | 24 | 3 | 2022-01-01 | 2021-12-26 | 2022-01-01 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Technology Stack | 4 | Dharmit Panchal | 12 | 150
3 | Timesheet 2022-01-02 | 1 | 1 | 22 | 2 | 2022-01-02 | 2022-01-02 | 2022-01-02 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Database Selection | 3 | Vatsal Prajapati | 12 | 100
4 | Timesheet 2022-01-07 | 1 | 1 | 21 | 4 | 2022-01-07 | 2022-01-02 | 2022-01-07 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Work Flow | 4 | Deepkumar Patel | 12 | 200
5 | Timesheet 2022-01-08 | 1 | 1 | 20 | 1 | 2022-01-08 | 2022-01-02 | 2022-01-08 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Setup in all the member's local machine | 1 | Vatsal Prajapati | 12 | 50
6 | Timesheet 2022-01-17 | 1 | 1 | 28 | 10 | 2022-01-17 | 2022-01-16 | 2022-01-17 | Dharmit Panchal | Vatsal Prajapati | Requirements | Requirements | Data Collection | 8 | Deepkumar Patel | 12 | 500
8 | Timesheet 2022-01-26 | 1 | 1 | 27 | 12 | 2022-01-25 | 2022-01-23 | 2022-01-25 | Vatsal Prajapati | Vatsal Prajapati | Requirements | Requirements | Data Cleaning and Manipulation | 7 | Dharmit Panchal | 12 | 600
9 | Timesheet 2022-02-02 | 29 | 29 | 2 | 4 | 2022-01-28 | 2022-01-23 | 2022-01-28 | Vatsal Prajapati | Vatsal Prajapati | Design | Design | Web Scraper Creation | 5 | Vatsal Prajapati | 12 | 200
10 | Timesheet 2022-02-02 | 29 | 29 | 39 | 2 | 2022-01-29 | 2022-01-23 | 2022-01-29 | Vatsal Prajapati | Vatsal Prajapati | Design | Design | Desing Analytics Model | 7 | Deepkumar Patel | 12 | 100
11 | Timesheet 2022-02-02 | 29 | 29 | 39 | 4 | 2022-01-30 | 2022-01-30 | 2022-01-30 | Vatsal Prajapati | Vatsal Prajapati | Design | Design | Desing Analytics Model | 7 | Dharmit Panchal | 12 | 200
12 | Timesheet 2022-02-09 | 30 | 31 | 31 | 1 | 2022-02-09 | 2022-02-06 | 2022-02-09 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Deepkumar Patel | 12 | 50
13 | Timesheet 2022-02-09 | 30 | 31 | 31 | 1 | 2022-02-09 | 2022-02-06 | 2022-02-09 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Dharmit Panchal | 12 | 50
14 | Timesheet 2022-02-09 | 30 | 31 | 31 | 2 | 2022-02-09 | 2022-02-06 | 2022-02-09 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Vatsal Prajapati | 12 | 100
15 | Timesheet 2022-02-16 | 30 | 31 | 31 | 3 | 2022-02-16 | 2022-02-13 | 2022-02-16 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Deepkumar Patel | 12 | 150
16 | Timesheet 2022-02-16 | 30 | 31 | 31 | 3 | 2022-02-16 | 2022-02-13 | 2022-02-16 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Dharmit Panchal | 12 | 150
17 | Timesheet 2022-02-16 | 30 | 31 | 31 | 4 | 2022-02-16 | 2022-02-13 | 2022-02-16 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Vatsal Prajapati | 12 | 200
18 | Timesheet 2022-02-23 | 30 | 31 | 31 | 3 | 2022-02-23 | 2022-02-20 | 2022-02-23 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Dharmit Panchal | 12 | 150
19 | Timesheet 2022-02-23 | 30 | 31 | 31 | 3 | 2022-02-23 | 2022-02-20 | 2022-02-23 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Deepkumar Patel | 12 | 150
20 | Timesheet 2022-02-23 | 30 | 31 | 31 | 4 | 2022-02-23 | 2022-02-20 | 2022-02-23 | Vatsal Prajapati | Vatsal Prajapati | Development | Develop an Analytics Model | Develop an Analytics Model | 24 | Vatsal Prajapati | 12 | 200

## Weekely Budgeted vs Actual
Row Labels | Average of Weekely Budgeted Hours | Sum of Hours
Vatsal Prajapati | 12 | 17
31-12-2021 - 06-01-2022 | 12 | 2
07-01-2022 - 13-01-2022 | 12 | 1
28-01-2022 - 03-02-2022 | 12 | 4
04-02-2022 - 10-02-2022 | 12 | 2
11-02-2022 - 17-02-2022 | 12 | 4
18-02-2022 - 24-02-2022 | 12 | 4
Grand Total | 12 | 17

## Current Cost of Project
Row Labels | Sum of Cost
Vatsal Prajapati | 850
Requirements | 150
Requirements | 150
Design | 200
Design | 200
Development | 500
Develop an Analytics Model | 500
Grand Total | 850

## Hours by Deliverable by Week
Row Labels | Sum of Hours
Design | 10
23-01-2022 - 29-01-2022 | 6
30-01-2022 - 05-02-2022 | 4
Requirements | 33
05-12-2021 - 11-12-2021 | 1
26-12-2021 - 01-01-2022 | 3
02-01-2022 - 08-01-2022 | 7
16-01-2022 - 22-01-2022 | 10
23-01-2022 - 29-01-2022 | 12
Development | 24
06-02-2022 - 12-02-2022 | 4
13-02-2022 - 19-02-2022 | 10
20-02-2022 - 21-02-2022 | 10
Grand Total | 67

## Project Cost by Person
Row Labels | Sum of Cost
Deepkumar Patel | 1200
Design | 100
Design | 100
Requirements | 750
Requirements | 750
Development | 350
Develop an Analytics Model | 350
Dharmit Panchal | 1300
Design | 200
Design | 200
Requirements | 750
Requirements | 750
Development | 350
Develop an Analytics Model | 350
Vatsal Prajapati | 850
Design | 200
Design | 200
Requirements | 150
Requirements | 150
Development | 500
Develop an Analytics Model | 500
Grand Total | 3350

## Task Budget vs Actual
Row Labels | Sum of Hours | Average of Task.Budgeted Hours
Design | 10 | 6.3333
Design | 10 | 6.3333
Desing Analytics Model | 6 | 7
Web Scraper Creation | 4 | 5
Requirements | 33 | 4
Requirements | 33 | 4
Client Acceptance of the project charter | 1 | 1
Data Cleaning and Manipulation | 12 | 7
Data Collection | 10 | 8
Database Selection | 2 | 3
Setup in all the member's local machine | 1 | 1
Technology Stack | 3 | 4
Work Flow | 4 | 4
Development | 24 | 24
Develop an Analytics Model | 24 | 24
Develop an Analytics Model | 24 | 24
Grand Total | 67 | 13.8421

## Resource Usage by Week and Task
Row Labels | Sum of Hours
Vatsal Prajapati | 17
31-12-2021 - 06-01-2022 | 2
Database Selection | 2
07-01-2022 - 13-01-2022 | 1
Setup in all the member's local machine | 1
28-01-2022 - 03-02-2022 | 4
Web Scraper Creation | 4
04-02-2022 - 10-02-2022 | 2
Develop an Analytics Model | 2
11-02-2022 - 17-02-2022 | 4
Develop an Analytics Model | 4
18-02-2022 - 24-02-2022 | 4
Develop an Analytics Model | 4
Grand Total | 17