## Dashboard
2021S Project Dashboard

## PPT Charts
Row Labels | Total Hours Spent | Weekly Hours Spent
Mit Chauhan | 73 | 8
<11-05-21 | 1 | 8
11-05-21 - 17-05-21 | 8 | 8
18-05-21 - 24-05-21 | 6 | 8
25-05-21 - 31-05-21 | 6 | 8
01-06-21 - 07-06-21 | 3 | 8
08-06-21 - 14-06-21 | 6.5 | 8
15-06-21 - 21-06-21 | 5.5 | 8
22-06-21 - 28-06-21 | 2.5 | 8
29-06-21 - 05-07-21 | 6.5 | 8
06-07-21 - 12-07-21 | 5 | 8
13-07-21 - 19-07-21 | 6 | 8
20-07-21 - 26-07-21 | 7 | 8
27-07-21 - 02-08-21 | 6 | 8
03-08-21 - 09-08-21 | 4 | 8
Grand Total | 73 | 8
Row Labels | Total Cost
Mit Chauhan | 3650
<11-05-21 | 50
11-05-21 - 17-05-21 | 400
18-05-21 - 24-05-21 | 300
25-05-21 - 31-05-21 | 300
01-06-21 - 07-06-21 | 150
08-06-21 - 14-06-21 | 325
15-06-21 - 21-06-21 | 275
22-06-21 - 28-06-21 | 125
29-06-21 - 05-07-21 | 325
06-07-21 - 12-07-21 | 250
13-07-21 - 19-07-21 | 300
20-07-21 - 26-07-21 | 350
27-07-21 - 02-08-21 | 300
03-08-21 - 09-08-21 | 200
Grand Total | 3650
Row Labels | Total Hours | Weekly Hours
<11-05-21 | 3 | 24
11-05-21 - 17-05-21 | 25 | 24
18-05-21 - 24-05-21 | 18 | 24
25-05-21 - 31-05-21 | 21 | 24
01-06-21 - 07-06-21 | 16 | 24
08-06-21 - 14-06-21 | 18.5 | 24
15-06-21 - 21-06-21 | 16.5 | 24
22-06-21 - 28-06-21 | 12.5 | 24
29-06-21 - 05-07-21 | 20.5 | 24
06-07-21 - 12-07-21 | 21 | 24
13-07-21 - 19-07-21 | 24 | 24
20-07-21 - 26-07-21 | 26 | 24
27-07-21 - 02-08-21 | 21 | 24
03-08-21 - 09-08-21 | 14 | 24
Grand Total | 257 | 24
Row Labels | Sum of Cost
<11-05-21 | 150
11-05-21 - 17-05-21 | 1250
18-05-21 - 24-05-21 | 900
25-05-21 - 31-05-21 | 1050
01-06-21 - 07-06-21 | 800
08-06-21 - 14-06-21 | 925
15-06-21 - 21-06-21 | 825
22-06-21 - 28-06-21 | 625
29-06-21 - 05-07-21 | 1025
06-07-21 - 12-07-21 | 1050
13-07-21 - 19-07-21 | 1200
20-07-21 - 26-07-21 | 1300
27-07-21 - 02-08-21 | 1050
03-08-21 - 09-08-21 | 700
Grand Total | 12850
Actual Cost | Projected Cost till Date
12850 | 14400

## Timesheet Data
Id | ID.1 | Title | AuthorId | EditorId | DeliverableId | Project PhaseId | TaskId | Assigned ToId | Hours | Task Date | Start of Week | End of Task | Author.Title | Editor.Title | Deliverable.Title | Project Phase.Title | Task.Title | Task.Budgeted Hours | Assigned To.Title | Weekly Budgeted Hours | Cost | Weekly Hours Per Person | Weekly Total Hours | Projected Cost
1 | 1 | Timesheet 2021-05-11 | 45 | 45 | 79 | 72 | 11 | 45 | 2 | 2021-05-11 | 2021-05-11 | 2021-05-11 | Mit Chauhan | Mit Chauhan | Project Workspace Set up | Requirements | Complete setting up the previous team’s system on the local systems | 6 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
2 | 2 | Timesheet 2021-05-12 | 45 | 45 | 79 | 72 | 11 | 44 | 2 | 2021-05-12 | 2021-05-11 | 2021-05-12 | Mit Chauhan | Mit Chauhan | Project Workspace Set up | Requirements | Complete setting up the previous team’s system on the local systems | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
3 | 3 | Timesheet 2021-05-11 | 45 | 45 | 79 | 72 | 11 | 43 | 2 | 2021-05-11 | 2021-05-11 | 2021-05-11 | Mit Chauhan | Mit Chauhan | Project Workspace Set up | Requirements | Complete setting up the previous team’s system on the local systems | 6 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
5 | 5 | Timesheet 2021-05-14 | 45 | 45 | 70 | 75 | 13 | 43 | 5 | 2021-05-14 | 2021-05-11 | 2021-05-14 | Mit Chauhan | Mit Chauhan | Database | Requirements | Complete understanding of the database schema of both website | 13 | Himanshu Limbasiya | 20 | 250 | 8 | 24 | 14400
6 | 6 | Timesheet 2021-05-15 | 45 | 45 | 71 | 80 | 13 | 45 | 4 | 2021-05-15 | 2021-05-11 | 2021-05-15 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Complete understanding of the database schema of both website | 13 | Mit Chauhan | 20 | 200 | 8 | 24 | 14400
8 | 8 | Timesheet 2021-05-17 | 45 | 45 | 70 | 75 | 13 | 44 | 4 | 2021-05-17 | 2021-05-18 | 2021-05-17 | Mit Chauhan | Mit Chauhan | Database | Requirements | Complete understanding of the database schema of both website | 13 | Pulkit Yadav | 20 | 200 | 8 | 24 | 14400
10 | 10 | Timesheet 2021-05-19 | 45 | 45 | 71 | 80 | 12 | 43 | 3 | 2021-05-19 | 2021-05-18 | 2021-05-19 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Identifying enhancements | 11 | Himanshu Limbasiya | 20 | 150 | 8 | 24 | 14400
14 | 14 | Timesheet 2021-05-21 | 45 | 45 | 71 | 80 | 12 | 45 | 3 | 2021-05-19 | 2021-05-18 | 2021-05-19 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Identifying enhancements | 11 | Mit Chauhan | 20 | 150 | 8 | 24 | 14400
15 | 15 | Timesheet 2021-05-21 | 45 | 45 | 71 | 80 | 12 | 44 | 3 | 2021-05-19 | 2021-05-18 | 2021-05-19 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Identifying enhancements | 11 | Pulkit Yadav | 20 | 150 | 8 | 24 | 14400
16 | 16 | Timesheet 2021-05-26 | 43 | 45 | 71 | 92 | 44 | 43 | 1 | 2021-05-26 | 2021-05-25 | 2021-05-26 | Himanshu Limbasiya | Mit Chauhan | Website Enhancements | Design | Home Page | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
17 | 17 | Timesheet 2021-05-29 | 43 | 45 | 71 | 92 | 39 | 43 | 1.5 | 2021-05-29 | 2021-05-25 | 2021-05-29 | Himanshu Limbasiya | Mit Chauhan | Website Enhancements | Design | Search Results Page | 6 | Himanshu Limbasiya | 20 | 75 | 8 | 24 | 14400
18 | 18 | Timesheet 2021-05-24 | 45 | 45 | 71 | 92 | 32 | 45 | 2 | 2021-05-24 | 2021-05-25 | 2021-05-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Landing Page | 4 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
19 | 19 | Timesheet 2021-05-25 | 45 | 45 | 71 | 92 | 33 | 45 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Login Page | 1 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
20 | 20 | Timesheet 2021-05-26 | 45 | 45 | 71 | 92 | 44 | 45 | 1 | 2021-05-26 | 2021-05-25 | 2021-05-26 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Home Page | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
21 | 21 | Timesheet 2021-05-27 | 45 | 45 | 71 | 92 | 35 | 45 | 1 | 2021-05-27 | 2021-05-25 | 2021-05-27 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Profile Page | 2 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
22 | 22 | Timesheet 2021-05-29 | 45 | 45 | 71 | 92 | 39 | 45 | 2 | 2021-05-29 | 2021-05-25 | 2021-05-29 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Search Results Page | 6 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
23 | 23 | Timesheet 2021-05-24 | 45 | 45 | 71 | 92 | 32 | 44 | 2 | 2021-05-24 | 2021-05-25 | 2021-05-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Landing Page | 4 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
24 | 24 | Timesheet 2021-05-25 | 45 | 45 | 71 | 73 | 34 | 44 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Register Page | 1 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
25 | 25 | Timesheet 2021-05-27 | 45 | 45 | 71 | 73 | 42 | 44 | 0.5 | 2021-05-27 | 2021-05-25 | 2021-05-27 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Verification Email Popup | 0.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
26 | 26 | Timesheet 2021-05-25 | 45 | 45 | 71 | 73 | 38 | 44 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Email Verified Page | 1 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
27 | 27 | Timesheet 2021-05-26 | 45 | 45 | 71 | 73 | 44 | 44 | 1 | 2021-05-26 | 2021-05-25 | 2021-05-26 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Home Page | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
28 | 28 | Timesheet 2021-05-27 | 45 | 45 | 71 | 73 | 40 | 44 | 0.5 | 2021-05-27 | 2021-05-25 | 2021-05-27 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Forgot Password Pop up | 0.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
29 | 29 | Timesheet 2021-05-28 | 45 | 45 | 71 | 73 | 37 | 44 | 1 | 2021-05-28 | 2021-05-25 | 2021-05-28 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Settings Page | 1.5 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
30 | 30 | Timesheet 2021-05-28 | 45 | 45 | 71 | 73 | 36 | 44 | 1 | 2021-05-28 | 2021-05-25 | 2021-05-28 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Reset Password Page | 1 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
31 | 31 | Timesheet 2021-05-28 | 45 | 45 | 71 | 73 | 41 | 44 | 0.5 | 2021-05-28 | 2021-05-25 | 2021-05-28 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Reset Confirmation Popup | 0.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
32 | 32 | Timesheet 2021-05-29 | 45 | 45 | 71 | 73 | 39 | 44 | 2 | 2021-05-29 | 2021-05-25 | 2021-05-29 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Search Results Page | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
33 | 33 | Timesheet 2021-05-25 | 45 | 45 | 26 | 28 | 69 | 45 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 2 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
34 | 34 | Timesheet 2021-05-25 | 45 | 45 | 26 | 28 | 69 | 43 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 2 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
35 | 35 | Timesheet 2021-05-25 | 45 | 45 | 26 | 28 | 69 | 44 | 1 | 2021-05-25 | 2021-05-25 | 2021-05-25 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 2 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
36 | 36 | Timesheet 2021-05-24 | 45 | 45 | 26 | 105 | 121 | 45 | 1 | 2021-05-24 | 2021-05-25 | 2021-05-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Week 5 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
37 | 37 | Timesheet 2021-05-24 | 45 | 45 | 26 | 105 | 106 | 43 | 2 | 2021-05-24 | 2021-05-25 | 2021-05-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 2 | 6 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
38 | 38 | Timesheet 2021-05-24 | 45 | 45 | 26 | 105 | 106 | 44 | 2 | 2021-05-24 | 2021-05-25 | 2021-05-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 2 | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
40 | 40 | Timesheet 2021-05-30 | 43 | 45 | 70 | 73 | 107 | 43 | 1 | 2021-05-30 | 2021-06-01 | 2021-05-30 | Himanshu Limbasiya | Mit Chauhan | Database | Design | Database schema design | 13 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
41 | 41 | Timesheet 2021-05-31 | 43 | 45 | 70 | 73 | 107 | 43 | 1 | 2021-05-31 | 2021-06-01 | 2021-05-31 | Himanshu Limbasiya | Mit Chauhan | Database | Design | Database schema design | 13 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
42 | 42 | Timesheet 2021-06-01 | 43 | 43 | 70 | 73 | 107 | 43 | 2 | 2021-06-01 | 2021-06-01 | 2021-06-01 | Himanshu Limbasiya | Himanshu Limbasiya | Database | Design | Database schema design | 13 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
43 | 43 | Timesheet 2021-06-02 | 45 | 45 | 71 | 92 | 113 | 43 | 1 | 2021-06-02 | 2021-06-01 | 2021-06-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Finalizing Bootstrap Templates | 4 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
44 | 44 | Timesheet 2021-06-02 | 45 | 45 | 71 | 73 | 113 | 44 | 2 | 2021-06-02 | 2021-06-01 | 2021-06-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Finalizing Bootstrap Templates | 4 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
45 | 45 | Timesheet 2021-06-01 | 45 | 45 | 26 | 28 | 58 | 45 | 1 | 2021-06-01 | 2021-06-01 | 2021-06-01 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 3 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
46 | 46 | Timesheet 2021-06-01 | 45 | 45 | 26 | 28 | 58 | 43 | 1 | 2021-06-01 | 2021-06-01 | 2021-06-01 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 3 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
47 | 47 | Timesheet 2021-06-01 | 45 | 45 | 26 | 28 | 58 | 44 | 1 | 2021-06-01 | 2021-06-01 | 2021-06-01 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 3 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
48 | 48 | Timesheet 2021-05-10 | 45 | 45 | 26 | 28 | 30 | 45 | 1 | 2021-05-10 | 2021-05-11 | 2021-05-10 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 1 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
49 | 49 | Timesheet 2021-05-10 | 45 | 45 | 26 | 28 | 30 | 43 | 1 | 2021-05-10 | 2021-05-11 | 2021-05-10 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 1 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
50 | 50 | Timesheet 2021-05-10 | 45 | 45 | 26 | 28 | 30 | 44 | 1 | 2021-05-10 | 2021-05-11 | 2021-05-10 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 1 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
51 | 51 | Timesheet 2021-05-15 | 45 | 45 | 26 | 105 | 111 | 45 | 2 | 2021-05-15 | 2021-05-11 | 2021-05-15 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 1 | 6 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
52 | 52 | Timesheet 2021-05-15 | 45 | 45 | 26 | 105 | 111 | 43 | 2 | 2021-05-15 | 2021-05-11 | 2021-05-15 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 1 | 6 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
53 | 53 | Timesheet 2021-05-15 | 45 | 45 | 26 | 105 | 111 | 44 | 2 | 2021-05-15 | 2021-05-11 | 2021-05-15 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 1 | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
54 | 54 | Timesheet 2021-06-04 | 43 | 43 | 70 | 74 | 112 | 43 | 2 | 2021-06-04 | 2021-06-01 | 2021-06-04 | Himanshu Limbasiya | Himanshu Limbasiya | Database | Development | Move data from SQLite to Local DB | 10 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
55 | 55 | Timesheet 2021-06-05 | 43 | 43 | 70 | 74 | 112 | 43 | 2 | 2021-06-05 | 2021-06-01 | 2021-06-05 | Himanshu Limbasiya | Himanshu Limbasiya | Database | Development | Move data from SQLite to Local DB | 10 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
56 | 56 | Timesheet 2021-06-07 | 45 | 45 | 71 | 92 | 113 | 44 | 2 | 2021-06-07 | 2021-06-08 | 2021-06-07 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Finalizing Bootstrap Templates | 4 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
57 | 57 | Timesheet 2021-06-07 | 45 | 45 | 71 | 73 | 113 | 45 | 2 | 2021-06-07 | 2021-06-08 | 2021-06-07 | Mit Chauhan | Mit Chauhan | Website Enhancements | Design | Finalizing Bootstrap Templates | 4 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
58 | 58 | Timesheet 2021-06-08 | 45 | 45 | 26 | 28 | 120 | 45 | 1 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 4 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
59 | 59 | Timesheet 2021-06-08 | 45 | 45 | 26 | 28 | 120 | 44 | 1 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 4 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
60 | 60 | Timesheet 2021-06-08 | 45 | 45 | 26 | 28 | 120 | 43 | 1 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 4 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
61 | 61 | Timesheet 2021-06-08 | 45 | 45 | 26 | 105 | 129 | 45 | 0.5 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 4 | 1.5 | Mit Chauhan | 20 | 25 | 8 | 24 | 14400
62 | 62 | Timesheet 2021-06-08 | 45 | 45 | 26 | 105 | 129 | 44 | 0.5 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 4 | 1.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
63 | 63 | Timesheet 2021-06-08 | 45 | 45 | 26 | 105 | 129 | 43 | 0.5 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 4 | 1.5 | Himanshu Limbasiya | 20 | 25 | 8 | 24 | 14400
64 | 64 | Timesheet 2021-06-10 | 45 | 45 | 26 | 105 | 130 | 45 | 1 | 2021-06-10 | 2021-06-08 | 2021-06-10 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 5 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
65 | 65 | Timesheet 2021-06-10 | 45 | 45 | 26 | 105 | 130 | 44 | 1 | 2021-06-10 | 2021-06-08 | 2021-06-10 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 5 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
66 | 66 | Timesheet 2021-06-10 | 45 | 45 | 26 | 105 | 130 | 43 | 1 | 2021-06-10 | 2021-06-08 | 2021-06-10 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 5 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
67 | 67 | Timesheet 2021-06-08 | 45 | 45 | 71 | 99 | 47 | 44 | 3 | 2021-06-08 | 2021-06-08 | 2021-06-08 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Landing Page Development | 6 | Pulkit Yadav | 20 | 150 | 8 | 24 | 14400
68 | 68 | Timesheet 2021-06-09 | 45 | 45 | 71 | 74 | 49 | 43 | 2 | 2021-06-09 | 2021-06-08 | 2021-06-09 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Login Page Development | 3 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
69 | 69 | Timesheet 2021-06-11 | 45 | 45 | 71 | 74 | 48 | 43 | 2 | 2021-06-11 | 2021-06-08 | 2021-06-11 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Register Page Development | 3 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
70 | 70 | Timesheet 2021-06-13 | 45 | 45 | 71 | 80 | 131 | 45 | 4 | 2021-06-13 | 2021-06-15 | 2021-06-13 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Requirement Documentation | 5 | Mit Chauhan | 20 | 200 | 8 | 24 | 14400
71 | 71 | Timesheet 2021-06-15 | 45 | 45 | 26 | 28 | 121 | 45 | 1 | 2021-06-15 | 2021-06-15 | 2021-06-15 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 5 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
72 | 72 | Timesheet 2021-05-15 | 45 | 45 | 26 | 28 | 121 | 43 | 1 | 2021-06-15 | 2021-06-15 | 2021-06-15 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 5 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
73 | 73 | Timesheet 2021-05-15 | 45 | 45 | 26 | 28 | 121 | 44 | 1 | 2021-06-15 | 2021-06-15 | 2021-06-15 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 5 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
74 | 74 | Timesheet 2021-06-17 | 45 | 45 | 26 | 28 | 132 | 45 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | New direction discussion meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
75 | 75 | Timesheet 2021-06-17 | 45 | 45 | 26 | 28 | 132 | 43 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | New direction discussion meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
76 | 76 | Timesheet 2021-06-17 | 45 | 45 | 26 | 28 | 132 | 44 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | New direction discussion meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
77 | 77 | Timesheet 2021-06-17 | 45 | 45 | 26 | 105 | 134 | 44 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 6 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
78 | 78 | Timesheet 2021-06-17 | 45 | 45 | 26 | 105 | 134 | 45 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 6 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
79 | 79 | Timesheet 2021-06-17 | 45 | 45 | 26 | 105 | 134 | 43 | 1 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 6 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
80 | 80 | Timesheet 2021-06-20 | 45 | 45 | 26 | 105 | 133 | 43 | 0.5 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 7 | 1.5 | Himanshu Limbasiya | 20 | 25 | 8 | 24 | 14400
81 | 81 | Timesheet 2021-06-20 | 45 | 45 | 26 | 105 | 133 | 44 | 0.5 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 7 | 1.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
82 | 82 | Timesheet 2021-06-20 | 45 | 45 | 26 | 105 | 133 | 45 | 0.5 | 2021-06-17 | 2021-06-15 | 2021-06-17 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 7 | 1.5 | Mit Chauhan | 20 | 25 | 8 | 24 | 14400
83 | 83 | Timesheet 2021-06-18 | 45 | 45 | 137 | 138 | 138 | 43 | 2 | 2021-06-18 | 2021-06-15 | 2021-06-18 | Mit Chauhan | Mit Chauhan |  |  |  |  | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
84 | 84 | Timesheet 2021-06-18 | 45 | 45 | 137 | 72 | 138 | 45 | 2 | 2021-06-18 | 2021-06-15 | 2021-06-18 | Mit Chauhan | Mit Chauhan |  | Requirements |  |  | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
85 | 85 | Timesheet 2021-06-19 | 45 | 45 | 137 | 72 | 138 | 44 | 2 | 2021-06-18 | 2021-06-15 | 2021-06-18 | Mit Chauhan | Mit Chauhan |  | Requirements |  |  | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
86 | 86 | Timesheet 2021-06-22 | 45 | 45 | 26 | 28 | 122 | 45 | 1 | 2021-06-22 | 2021-06-22 | 2021-06-22 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 6 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
87 | 87 | Timesheet 2021-06-22 | 45 | 45 | 26 | 28 | 122 | 44 | 1 | 2021-06-22 | 2021-06-22 | 2021-06-22 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 6 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
88 | 88 | Timesheet 2021-06-22 | 45 | 45 | 26 | 28 | 122 | 43 | 1 | 2021-06-22 | 2021-06-22 | 2021-06-22 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 6 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
89 | 89 | Timesheet 2021-06-27 | 45 | 45 | 26 | 105 | 139 | 45 | 1 | 2021-06-27 | 2021-06-29 | 2021-06-27 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 9 | 2 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
90 | 90 | Timesheet 2021-06-27 | 45 | 45 | 26 | 105 | 139 | 44 | 1 | 2021-06-27 | 2021-06-29 | 2021-06-27 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 9 | 2 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
91 | 91 | Timesheet 2021-06-30 | 45 | 45 | 137 | 72 | 72 | 45 | 3 | 2021-06-30 | 2021-06-29 | 2021-06-30 | Mit Chauhan | Mit Chauhan |  | Requirements | Requirements |  | Mit Chauhan | 20 | 150 | 8 | 24 | 14400
92 | 92 | Timesheet 2021-06-30 | 45 | 45 | 137 | 72 | 72 | 44 | 3 | 2021-06-30 | 2021-06-29 | 2021-06-30 | Mit Chauhan | Mit Chauhan |  | Requirements | Requirements |  | Pulkit Yadav | 20 | 150 | 8 | 24 | 14400
93 | 93 | Timesheet 2021-06-24 | 45 | 45 | 71 | 99 | 47 | 43 | 3 | 2021-06-24 | 2021-06-22 | 2021-06-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Landing Page Development | 6 | Himanshu Limbasiya | 20 | 150 | 8 | 24 | 14400
94 | 94 | Timesheet 2021-06-25 | 45 | 45 | 71 | 74 | 52 | 43 | 3 | 2021-06-25 | 2021-06-22 | 2021-06-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Himanshu Limbasiya | 20 | 150 | 8 | 24 | 14400
95 | 95 | Timesheet 2021-07-01 | 45 | 45 | 71 | 74 | 52 | 43 | 3 | 2021-07-01 | 2021-06-29 | 2021-07-01 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Himanshu Limbasiya | 20 | 150 | 8 | 24 | 14400
96 | 96 | Timesheet 2021-07-02 | 45 | 45 | 71 | 74 | 51 | 43 | 4 | 2021-07-02 | 2021-06-29 | 2021-07-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Home Page Development | 9 | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
97 | 97 | Timesheet 2021-07-01 | 45 | 45 | 71 | 74 | 52 | 44 | 3 | 2021-07-01 | 2021-06-29 | 2021-07-01 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Pulkit Yadav | 20 | 150 | 8 | 24 | 14400
98 | 98 | Timesheet 2021-07-02 | 45 | 45 | 137 | 72 | 72 | 45 | 3 | 2021-07-02 | 2021-06-29 | 2021-07-02 | Mit Chauhan | Mit Chauhan |  | Requirements | Requirements |  | Mit Chauhan | 20 | 150 | 8 | 24 | 14400
99 | 99 | Timesheet 2021-06-24 | 45 | 45 | 26 | 105 | 140 | 45 | 0.5 | 2021-06-24 | 2021-06-22 | 2021-06-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 8 | 1.5 | Mit Chauhan | 20 | 25 | 8 | 24 | 14400
100 | 100 | Timesheet 2021-06-24 | 45 | 45 | 26 | 105 | 140 | 44 | 0.5 | 2021-06-24 | 2021-06-22 | 2021-06-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 8 | 1.5 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
101 | 101 | Timesheet 2021-06-24 | 45 | 45 | 26 | 105 | 140 | 43 | 0.5 | 2021-06-24 | 2021-06-22 | 2021-06-24 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 8 | 1.5 | Himanshu Limbasiya | 20 | 25 | 8 | 24 | 14400
102 | 102 | Timesheet 2021-06-29 | 45 | 45 | 26 | 105 | 141 | 45 | 0.5 | 2021-06-29 | 2021-06-29 | 2021-06-29 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Mit Chauhan | 20 | 25 | 8 | 24 | 14400
103 | 103 | Timesheet 2021-06-29 | 45 | 45 | 26 | 105 | 141 | 44 | 0.5 | 2021-06-29 | 2021-06-29 | 2021-06-29 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Pulkit Yadav | 20 | 25 | 8 | 24 | 14400
104 | 104 | Timesheet 2021-06-29 | 45 | 45 | 26 | 105 | 141 | 43 | 0.5 | 2021-06-29 | 2021-06-29 | 2021-06-29 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Himanshu Limbasiya | 20 | 25 | 8 | 24 | 14400
105 | 105 | Timesheet 2021-07-06 | 45 | 45 | 26 | 28 | 124 | 45 | 1 | 2021-07-06 | 2021-07-06 | 2021-07-06 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 8 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
106 | 106 | Timesheet 2021-07-06 | 45 | 45 | 26 | 28 | 124 | 44 | 1 | 2021-07-06 | 2021-07-06 | 2021-07-06 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 8 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
107 | 107 | Timesheet 2021-07-06 | 45 | 45 | 26 | 28 | 124 | 43 | 1 | 2021-07-06 | 2021-07-06 | 2021-07-06 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 8 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
112 | 112 | Timesheet 2021-07-07 | 45 | 45 | 71 | 99 | 53 | 43 | 4 | 2021-07-07 | 2021-07-06 | 2021-07-07 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Settings Page Development | 6 | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
113 | 113 | Timesheet 2021-07-08 | 45 | 45 | 71 | 74 | 53 | 44 | 2 | 2021-07-08 | 2021-07-06 | 2021-07-08 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Settings Page Development | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
114 | 114 | Timesheet 2021-07-10 | 45 | 45 | 71 | 74 | 55 | 43 | 4 | 2021-07-10 | 2021-07-06 | 2021-07-10 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Search Results Page Development | 8 | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
115 | 115 | Timesheet 2021-07-12 | 45 | 45 | 71 | 74 | 55 | 44 | 2 | 2021-07-12 | 2021-07-13 | 2021-07-12 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Search Results Page Development | 8 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
116 | 116 | Timesheet 2021-07-09 | 45 | 45 | 137 | 72 | 72 | 45 | 3 | 2021-07-09 | 2021-07-06 | 2021-07-09 | Mit Chauhan | Mit Chauhan |  | Requirements | Requirements |  | Mit Chauhan | 20 | 150 | 8 | 24 | 14400
117 | 117 | Timesheet 2021-07-07 | 45 | 45 | 26 | 105 | 141 | 43 | 1 | 2021-07-07 | 2021-07-06 | 2021-07-07 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
118 | 118 | Timesheet 2021-07-07 | 45 | 45 | 26 | 105 | 141 | 44 | 1 | 2021-07-07 | 2021-07-06 | 2021-07-07 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
119 | 119 | Timesheet 2021-07-07 | 45 | 45 | 26 | 105 | 141 | 45 | 1 | 2021-07-07 | 2021-07-06 | 2021-07-07 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 11 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
120 | 120 | Timesheet 2021-07-13 | 45 | 45 | 26 | 28 | 125 | 45 | 1 | 2021-07-13 | 2021-07-13 | 2021-07-13 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 9 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
121 | 121 | Timesheet 2021-07-13 | 45 | 45 | 26 | 28 | 125 | 44 | 1 | 2021-07-13 | 2021-07-13 | 2021-07-13 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 9 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
122 | 122 | Timesheet 2021-07-13 | 45 | 45 | 26 | 28 | 125 | 43 | 1 | 2021-07-13 | 2021-07-13 | 2021-07-13 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 9 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
123 | 123 | Timesheet 2021-07-15 | 45 | 45 | 71 | 99 | 51 | 43 | 5 | 2021-07-15 | 2021-07-13 | 2021-07-15 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Home Page Development | 9 | Himanshu Limbasiya | 20 | 250 | 8 | 24 | 14400
124 | 124 | Timesheet 2021-07-18 | 45 | 45 | 71 | 74 | 55 | 43 | 5 | 2021-07-18 | 2021-07-20 | 2021-07-18 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Search Results Page Development | 8 | Himanshu Limbasiya | 20 | 250 | 8 | 24 | 14400
125 | 125 | Timesheet 2021-07-15 | 45 | 45 | 71 | 74 | 51 | 44 | 2 | 2021-07-15 | 2021-07-13 | 2021-07-15 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Home Page Development | 9 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
126 | 126 | Timesheet 2021-07-15 | 45 | 45 | 71 | 74 | 51 | 45 | 2 | 2021-07-15 | 2021-07-13 | 2021-07-15 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Home Page Development | 9 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
127 | 127 | Timesheet 2021-07-17 | 45 | 45 | 71 | 74 | 55 | 45 | 2 | 2021-07-17 | 2021-07-13 | 2021-07-17 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Search Results Page Development | 8 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
128 | 128 | Timesheet 2021-07-17 | 45 | 45 | 71 | 74 | 55 | 44 | 2 | 2021-07-17 | 2021-07-13 | 2021-07-17 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Search Results Page Development | 8 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
129 | 129 | Timesheet 2021-07-14 | 45 | 45 | 26 | 105 | 143 | 45 | 1 | 2021-07-14 | 2021-07-13 | 2021-07-14 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 12 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
130 | 130 | Timesheet 2021-07-14 | 45 | 45 | 26 | 105 | 143 | 43 | 1 | 2021-07-14 | 2021-07-13 | 2021-07-14 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 12 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
131 | 131 | Timesheet 2021-07-14 | 45 | 45 | 26 | 105 | 143 | 44 | 1 | 2021-07-14 | 2021-07-13 | 2021-07-14 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 12 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
132 | 132 | Timesheet 2021-07-20 | 45 | 45 | 26 | 28 | 126 | 45 | 1 | 2021-07-20 | 2021-07-20 | 2021-07-20 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 10 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
133 | 133 | Timesheet 2021-07-20 | 45 | 45 | 26 | 28 | 126 | 44 | 1 | 2021-07-20 | 2021-07-20 | 2021-07-20 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 10 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
134 | 134 | Timesheet 2021-07-20 | 45 | 45 | 26 | 28 | 126 | 43 | 1 | 2021-07-20 | 2021-07-20 | 2021-07-20 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 10 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
135 | 135 | Timesheet 2021-07-21 | 45 | 45 | 26 | 105 | 144 | 44 | 1 | 2021-07-21 | 2021-07-20 | 2021-07-21 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 13 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
136 | 136 | Timesheet 2021-07-21 | 45 | 45 | 26 | 105 | 144 | 43 | 1 | 2021-07-21 | 2021-07-20 | 2021-07-21 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 13 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
137 | 137 | Timesheet 2021-07-21 | 45 | 45 | 26 | 105 | 144 | 45 | 1 | 2021-07-21 | 2021-07-20 | 2021-07-21 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 13 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
138 | 138 | Timesheet 2021-07-22 | 45 | 45 | 71 | 74 | 52 | 43 | 4 | 2021-07-22 | 2021-07-20 | 2021-07-22 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
139 | 139 | Timesheet 2021-07-24 | 45 | 45 | 71 | 74 | 52 | 43 | 4 | 2021-07-24 | 2021-07-20 | 2021-07-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
140 | 140 | Timesheet 2021-07-26 | 45 | 45 | 71 | 74 | 52 | 43 | 2 | 2021-07-26 | 2021-07-27 | 2021-07-26 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
141 | 141 | Timesheet 2021-07-25 | 45 | 45 | 71 | 97 | 145 | 45 | 2 | 2021-07-25 | 2021-07-27 | 2021-07-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Release | Recommendations/Suggestions | 4 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
142 | 142 | Timesheet 2021-07-25 | 45 | 45 | 71 | 97 | 145 | 44 | 2 | 2021-07-25 | 2021-07-27 | 2021-07-25 | Mit Chauhan | Mit Chauhan | Website Enhancements | Release | Recommendations/Suggestions | 4 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
143 | 143 | Timesheet 2021-07-24 | 45 | 45 | 71 | 75 | 131 | 45 | 1 | 2021-07-24 | 2021-07-20 | 2021-07-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Requirement Documentation | 5 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
144 | 144 | Timesheet 2021-07-24 | 45 | 45 | 71 | 72 | 131 | 44 | 1 | 2021-07-24 | 2021-07-20 | 2021-07-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Requirements | Requirement Documentation | 5 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
145 | 145 | Timesheet 2021-07-24 | 45 | 45 | 71 | 74 | 52 | 45 | 2 | 2021-07-24 | 2021-07-20 | 2021-07-24 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
146 | 146 | Timesheet 2021-07-26 | 45 | 45 | 71 | 74 | 52 | 44 | 2 | 2021-07-26 | 2021-07-27 | 2021-07-26 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Profile Page Development | 9 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
147 | 147 | Timesheet 2021-07-28 | 45 | 45 | 71 | 74 | 50 | 43 | 2 | 2021-07-28 | 2021-07-27 | 2021-07-28 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Email verified Page Development | 3 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
148 | 148 | Timesheet 2021-07-30 | 45 | 45 | 71 | 74 | 53 | 43 | 2 | 2021-07-30 | 2021-07-27 | 2021-07-30 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Settings Page Development | 6 | Himanshu Limbasiya | 20 | 100 | 8 | 24 | 14400
149 | 149 | Timesheet 2021-07-30 | 45 | 45 | 71 | 74 | 146 | 43 | 3 | 2021-07-30 | 2021-07-27 | 2021-07-30 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Hosting the website | 8 | Himanshu Limbasiya | 20 | 150 | 8 | 24 | 14400
150 | 150 | Timesheet 2021-07-31 | 45 | 45 | 71 | 98 | 24 | 45 | 2 | 2021-07-31 | 2021-07-27 | 2021-07-31 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Testing with Georgian students |  | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
151 | 151 | Timesheet 2021-07-31 | 45 | 45 | 71 | 98 | 24 | 44 | 2 | 2021-07-31 | 2021-07-27 | 2021-07-31 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Testing with Georgian students |  | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
152 | 152 | Timesheet 2021-07-29 | 45 | 45 | 71 | 99 | 47 | 45 | 2 | 2021-07-29 | 2021-07-27 | 2021-07-29 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Landing Page Development | 6 | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
153 | 153 | Timesheet 2021-07-29 | 45 | 45 | 71 | 74 | 47 | 44 | 2 | 2021-07-29 | 2021-07-27 | 2021-07-29 | Mit Chauhan | Mit Chauhan | Website Enhancements | Development | Landing Page Development | 6 | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
154 | 154 | Timesheet 2021-07-28 | 45 | 45 | 26 | 105 | 147 | 45 | 1 | 2021-07-28 | 2021-07-27 | 2021-07-28 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 14 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
155 | 155 | Timesheet 2021-07-28 | 45 | 45 | 26 | 105 | 147 | 44 | 1 | 2021-07-28 | 2021-07-27 | 2021-07-28 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 14 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
156 | 156 | Timesheet 2021-07-28 | 45 | 45 | 26 | 105 | 147 | 43 | 1 | 2021-07-28 | 2021-07-27 | 2021-07-28 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 14 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
157 | 157 | Timesheet 2021-08-03 | 45 | 45 | 26 | 28 | 128 | 45 | 1 | 2021-08-03 | 2021-08-03 | 2021-08-03 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 12 status meeting | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
158 | 158 | Timesheet 2021-08-03 | 45 | 45 | 26 | 28 | 128 | 44 | 1 | 2021-08-03 | 2021-08-03 | 2021-08-03 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 12 status meeting | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
159 | 159 | Timesheet 2021-08-03 | 45 | 45 | 26 | 28 | 128 | 43 | 1 | 2021-08-03 | 2021-08-03 | 2021-08-03 | Mit Chauhan | Mit Chauhan | Meetings | Client Meetings | Week 12 status meeting | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
160 | 160 | Timesheet 2021-08-02 | 45 | 45 | 71 | 98 | 24 | 45 | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Testing with Georgian students |  | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
161 | 161 | Timesheet 2021-08-02 | 45 | 45 | 71 | 98 | 24 | 43 | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Testing with Georgian students |  | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
162 | 162 | Timesheet 2021-08-02 | 45 | 45 | 71 | 98 | 24 | 44 | 1 | 2021-08-02 | 2021-08-03 | 2021-08-02 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Testing with Georgian students |  | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
164 | 164 | Timesheet 2021-08-06 | 45 | 45 | 71 | 98 | 149 | 45 | 2 | 2021-08-06 | 2021-08-03 | 2021-08-06 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Bug-fixes |  | Mit Chauhan | 20 | 100 | 8 | 24 | 14400
165 | 165 | Timesheet 2021-08-06 | 45 | 45 | 71 | 98 | 149 | 44 | 2 | 2021-08-06 | 2021-08-03 | 2021-08-06 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Bug-fixes |  | Pulkit Yadav | 20 | 100 | 8 | 24 | 14400
166 | 166 | Timesheet 2021-08-06 | 45 | 45 | 71 | 98 | 149 | 43 | 4 | 2021-08-06 | 2021-08-03 | 2021-08-06 | Mit Chauhan | Mit Chauhan | Website Enhancements | Testing | Bug-fixes |  | Himanshu Limbasiya | 20 | 200 | 8 | 24 | 14400
167 | 167 | Timesheet 2021-08-04 | 45 | 45 | 26 | 105 | 151 | 43 | 1 | 2021-08-04 | 2021-08-03 | 2021-08-04 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 15 | 3 | Himanshu Limbasiya | 20 | 50 | 8 | 24 | 14400
168 | 168 | Timesheet 2021-08-04 | 45 | 45 | 26 | 105 | 151 | 45 | 1 | 2021-08-04 | 2021-08-03 | 2021-08-04 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 15 | 3 | Mit Chauhan | 20 | 50 | 8 | 24 | 14400
169 | 169 | Timesheet 2021-08-04 | 45 | 45 | 26 | 105 | 151 | 44 | 1 | 2021-08-04 | 2021-08-03 | 2021-08-04 | Mit Chauhan | Mit Chauhan | Meetings | Team Meetings | Meeting 15 | 3 | Pulkit Yadav | 20 | 50 | 8 | 24 | 14400
12850

## Hours by Deliverable by Week
Row Labels | Sum of Hours
Project Workspace Set up | 6
11-05-21 - 17-05-21 | 6
Database | 17
11-05-21 - 17-05-21 | 5
18-05-21 - 24-05-21 | 4
01-06-21 - 07-06-21 | 8
Website Enhancements | 143
11-05-21 - 17-05-21 | 4
18-05-21 - 24-05-21 | 9
25-05-21 - 31-05-21 | 20
01-06-21 - 07-06-21 | 3
08-06-21 - 14-06-21 | 11
15-06-21 - 21-06-21 | 4
22-06-21 - 28-06-21 | 6
29-06-21 - 05-07-21 | 10
06-07-21 - 12-07-21 | 10
13-07-21 - 19-07-21 | 15
20-07-21 - 26-07-21 | 17
27-07-21 - 02-08-21 | 23
03-08-21 - 09-08-21 | 11
Meetings | 73
11-05-21 - 17-05-21 | 9
25-05-21 - 31-05-21 | 8
01-06-21 - 07-06-21 | 3
08-06-21 - 14-06-21 | 7.5
15-06-21 - 21-06-21 | 10.5
22-06-21 - 28-06-21 | 4.5
29-06-21 - 05-07-21 | 3.5
06-07-21 - 12-07-21 | 6
13-07-21 - 19-07-21 | 6
20-07-21 - 26-07-21 | 6
27-07-21 - 02-08-21 | 3
03-08-21 - 09-08-21 | 6
Grand Total | 239

## Project Cost Data
Assigned To.Title | Deliverable.Title | Project Phase.Title | Hours | Cost
Mit Chauhan | Project Workspace Set up | Requirements | 2 | 100
Pulkit Yadav | Project Workspace Set up | Requirements | 2 | 100
Himanshu Limbasiya | Project Workspace Set up | Requirements | 2 | 100
Himanshu Limbasiya | Database | Requirements | 5 | 250
Mit Chauhan | Website Enhancements | Requirements | 12 | 600
Pulkit Yadav | Database | Requirements | 4 | 200
Himanshu Limbasiya | Website Enhancements | Requirements | 3 | 150
Pulkit Yadav | Website Enhancements | Requirements | 4 | 200
Himanshu Limbasiya | Website Enhancements | Design | 4 | 175
Mit Chauhan | Website Enhancements | Design | 9 | 450
Pulkit Yadav | Website Enhancements | Design | 13 | 725
Mit Chauhan | Meetings | Client Meetings | 11 | 550
Himanshu Limbasiya | Meetings | Client Meetings | 11 | 550
Pulkit Yadav | Meetings | Client Meetings | 11 | 550
Mit Chauhan | Meetings | Team Meetings | 11 | 650
Himanshu Limbasiya | Meetings | Team Meetings | 11 | 650
Pulkit Yadav | Meetings | Team Meetings | 12 | 700
Himanshu Limbasiya | Database | Design | 4 | 200
Himanshu Limbasiya | Database | Development | 4 | 200
Pulkit Yadav | Website Enhancements | Development | 18 | 900
Himanshu Limbasiya | Website Enhancements | Development | 52 | 2600
Himanshu Limbasiya |  |  | 2 | 100
Mit Chauhan |  | Requirements | 11 | 550
Pulkit Yadav |  | Requirements | 5 | 250
Mit Chauhan | Website Enhancements | Development | 8 | 400
Mit Chauhan | Website Enhancements | Release | 2 | 100
Pulkit Yadav | Website Enhancements | Release | 2 | 100
Mit Chauhan | Website Enhancements | Testing | 5 | 250
Pulkit Yadav | Website Enhancements | Testing | 5 | 250
Himanshu Limbasiya | Website Enhancements | Testing | 5 | 250
12850

## Project Cost by Person Chart
Row Labels | Sum of Cost
Himanshu Limbasiya | 875
Project Workspace Set up | 100
Requirements | 100
Database | 450
Requirements | 250
Design | 200
Website Enhancements | 325
Requirements | 150
Design | 175
Mit Chauhan | 1150
Project Workspace Set up | 100
Requirements | 100
Website Enhancements | 1050
Requirements | 600
Design | 450
Pulkit Yadav | 1225
Project Workspace Set up | 100
Requirements | 100
Database | 200
Requirements | 200
Website Enhancements | 925
Requirements | 200
Design | 725
Grand Total | 3250

## Resourse Usage by Week and Task
Row Labels | Total Hours
Himanshu Limbasiya | 104.5
<11-05-21 | 1
Week 1 status meeting | 1
11-05-21 - 17-05-21 | 9
Complete setting up the previous team’s system on the local systems | 2
Complete understanding of the database schema of both website | 5
Meeting 1 | 2
18-05-21 - 24-05-21 | 5
Identifying enhancements | 3
Meeting 2 | 2
25-05-21 - 31-05-21 | 5.5
Home Page | 1
Search Results Page | 1.5
Week 2 status meeting | 1
Database schema design | 2
01-06-21 - 07-06-21 | 8
Database schema design | 2
Finalizing Bootstrap Templates | 1
Week 3 status meeting | 1
Move data from SQLite to Local DB | 4
08-06-21 - 14-06-21 | 6.5
Week 4 status meeting | 1
Meeting 4 | 0.5
Meeting 5 | 1
Login Page Development | 2
Register Page Development | 2
15-06-21 - 21-06-21 | 5.5
Week 5 status meeting | 1
New direction discussion meeting | 1
Meeting 6 | 1
Meeting 7 | 0.5
(blank) | 2
22-06-21 - 28-06-21 | 7.5
Landing Page Development | 3
Week 6 status meeting | 1
Meeting 8 | 0.5
Profile Page Development | 3
29-06-21 - 05-07-21 | 7.5
Profile Page Development | 3
Home Page Development | 4
Meeting 11 | 0.5
06-07-21 - 12-07-21 | 10
Meeting 11 | 1
Week 8 status meeting | 1
Settings Page Development | 4
Search Results Page Development | 4
13-07-21 - 19-07-21 | 12
Home Page Development | 5
Week 9 status meeting | 1
Search Results Page Development | 5
Meeting 12 | 1
20-07-21 - 26-07-21 | 12
Profile Page Development | 10
Meeting 13 | 1
Week 10 status meeting | 1
27-07-21 - 02-08-21 | 9
Settings Page Development | 2
Email verified Page Development | 2
Hosting the website | 3
Testing with Georgian students | 1
Meeting 14 | 1
03-08-21 - 09-08-21 | 6
Week 12 status meeting | 1
Bug-fixes | 4
Meeting 15 | 1
Mit Chauhan | 73
<11-05-21 | 1
Week 1 status meeting | 1
11-05-21 - 17-05-21 | 8
Complete setting up the previous team’s system on the local systems | 2
Complete understanding of the database schema of both website | 4
Meeting 1 | 2
18-05-21 - 24-05-21 | 6
Landing Page | 2
Identifying enhancements | 3
Week 5 status meeting | 1
25-05-21 - 31-05-21 | 6
Home Page | 1
Search Results Page | 2
Login Page | 1
Profile Page | 1
Week 2 status meeting | 1
01-06-21 - 07-06-21 | 3
Finalizing Bootstrap Templates | 2
Week 3 status meeting | 1
08-06-21 - 14-06-21 | 6.5
Week 4 status meeting | 1
Meeting 4 | 0.5
Meeting 5 | 1
Requirement Documentation | 4
15-06-21 - 21-06-21 | 5.5
Week 5 status meeting | 1
New direction discussion meeting | 1
Meeting 6 | 1
Meeting 7 | 0.5
(blank) | 2
22-06-21 - 28-06-21 | 2.5
Week 6 status meeting | 1
Meeting 8 | 0.5
Meeting 9 | 1
29-06-21 - 05-07-21 | 6.5
Requirements | 6
Meeting 11 | 0.5
06-07-21 - 12-07-21 | 5
Requirements | 3
Meeting 11 | 1
Week 8 status meeting | 1
13-07-21 - 19-07-21 | 6
Home Page Development | 2
Week 9 status meeting | 1
Search Results Page Development | 2
Meeting 12 | 1
20-07-21 - 26-07-21 | 7
Requirement Documentation | 1
Profile Page Development | 2
Meeting 13 | 1
Week 10 status meeting | 1
Recommendations/Suggestions | 2
27-07-21 - 02-08-21 | 6
Landing Page Development | 2
Testing with Georgian students | 3
Meeting 14 | 1
03-08-21 - 09-08-21 | 4
Week 12 status meeting | 1
Bug-fixes | 2
Meeting 15 | 1
Pulkit Yadav | 79.5
<11-05-21 | 1
Week 1 status meeting | 1
11-05-21 - 17-05-21 | 8
Complete setting up the previous team’s system on the local systems | 2
Complete understanding of the database schema of both website | 4
Meeting 1 | 2
18-05-21 - 24-05-21 | 7
Landing Page | 2
Identifying enhancements | 3
Meeting 2 | 2
25-05-21 - 31-05-21 | 9.5
Home Page | 1
Search Results Page | 2
Register Page | 1
Verification Email Popup | 0.5
Email Verified Page | 1
Forgot Password Pop up | 0.5
Settings Page | 1
Reset Password Page | 1
Reset Confirmation Popup | 0.5
Week 2 status meeting | 1
01-06-21 - 07-06-21 | 5
Finalizing Bootstrap Templates | 4
Week 3 status meeting | 1
08-06-21 - 14-06-21 | 5.5
Week 4 status meeting | 1
Meeting 4 | 0.5
Meeting 5 | 1
Landing Page Development | 3
15-06-21 - 21-06-21 | 5.5
Week 5 status meeting | 1
New direction discussion meeting | 1
Meeting 6 | 1
Meeting 7 | 0.5
(blank) | 2
22-06-21 - 28-06-21 | 2.5
Week 6 status meeting | 1
Meeting 8 | 0.5
Meeting 9 | 1
29-06-21 - 05-07-21 | 6.5
Requirements | 3
Profile Page Development | 3
Meeting 11 | 0.5
06-07-21 - 12-07-21 | 6
Meeting 11 | 1
Week 8 status meeting | 1
Settings Page Development | 2
Search Results Page Development | 2
13-07-21 - 19-07-21 | 6
Home Page Development | 2
Week 9 status meeting | 1
Search Results Page Development | 2
Meeting 12 | 1
20-07-21 - 26-07-21 | 7
Requirement Documentation | 1
Profile Page Development | 2
Meeting 13 | 1
Week 10 status meeting | 1
Recommendations/Suggestions | 2
27-07-21 - 02-08-21 | 6
Landing Page Development | 2
Testing with Georgian students | 3
Meeting 14 | 1
03-08-21 - 09-08-21 | 4
Week 12 status meeting | 1
Bug-fixes | 2
Meeting 15 | 1
Grand Total | 257

## Task Budget vs Actual Chart
Row Labels | Average of Task Budgeted Hours | Hours Spent
<11-05-21 | 3 | 3
Meetings | 3 | 3
Week 1 status meeting | 3 | 3
11-05-21 - 17-05-21 | 8.3333 | 25
Project Workspace Set up | 6 | 6
Complete setting up the previous team’s system on the local systems | 6 | 6
Database | 13 | 9
Complete understanding of the database schema of both website | 13 | 9
Website Enhancements | 13 | 4
Complete understanding of the database schema of both website | 13 | 4
Meetings | 6 | 6
Meeting 1 | 6 | 6
18-05-21 - 24-05-21 | 7 | 18
Website Enhancements | 8.2 | 13
Landing Page | 4 | 4
Identifying enhancements | 11 | 9
Meetings | 5 | 5
Meeting 2 | 6 | 4
Week 5 status meeting | 3 | 1
25-05-21 - 31-05-21 | 3.55 | 21
Database | 13 | 2
Database schema design | 13 | 2
Website Enhancements | 2.4 | 16
Home Page | 3 | 3
Search Results Page | 6 | 5.5
Login Page | 1 | 1
Profile Page | 2 | 1
Register Page | 1 | 1
Verification Email Popup | 0.5 | 0.5
Email Verified Page | 1 | 1
Forgot Password Pop up | 0.5 | 0.5
Settings Page | 1.5 | 1
Reset Password Page | 1 | 1
Reset Confirmation Popup | 0.5 | 0.5
Meetings | 3 | 3
Week 2 status meeting | 3 | 3
01-06-21 - 07-06-21 | 5.8 | 16
Database | 11 | 6
Database schema design | 13 | 2
Move data from SQLite to Local DB | 10 | 4
Website Enhancements | 4 | 7
Finalizing Bootstrap Templates | 4 | 7
Meetings | 3 | 3
Week 3 status meeting | 3 | 3
08-06-21 - 14-06-21 | 3.0385 | 18.5
Website Enhancements | 4.25 | 11
Landing Page Development | 6 | 3
Login Page Development | 3 | 2
Register Page Development | 3 | 2
Requirement Documentation | 5 | 4
Meetings | 2.5 | 7.5
Week 4 status meeting | 3 | 3
Meeting 4 | 1.5 | 1.5
Meeting 5 | 3 | 3
15-06-21 - 21-06-21 | 2.625 | 10.5
Meetings | 2.625 | 10.5
Week 5 status meeting | 3 | 3
New direction discussion meeting | 3 | 3
Meeting 6 | 3 | 3
Meeting 7 | 1.5 | 1.5
22-06-21 - 28-06-21 | 3.25 | 12.5
Website Enhancements | 7.5 | 6
Landing Page Development | 6 | 3
Profile Page Development | 9 | 3
Meetings | 2.1875 | 6.5
Week 6 status meeting | 3 | 3
Meeting 8 | 1.5 | 1.5
Meeting 9 | 2 | 2
29-06-21 - 05-07-21 | 6 | 11.5
Website Enhancements | 9 | 10
Profile Page Development | 9 | 6
Home Page Development | 9 | 4
Meetings | 3 | 1.5
Meeting 11 | 3 | 1.5
06-07-21 - 12-07-21 | 4.6 | 18
Website Enhancements | 7 | 12
Settings Page Development | 6 | 6
Search Results Page Development | 8 | 6
Meetings | 3 | 6
Meeting 11 | 3 | 3
Week 8 status meeting | 3 | 3
13-07-21 - 19-07-21 | 5.75 | 24
Website Enhancements | 8.5 | 18
Home Page Development | 9 | 9
Search Results Page Development | 8 | 9
Meetings | 3 | 6
Week 9 status meeting | 3 | 3
Meeting 12 | 3 | 3
20-07-21 - 26-07-21 | 5.4 | 26
Website Enhancements | 7 | 20
Requirement Documentation | 5 | 2
Profile Page Development | 9 | 14
Recommendations/Suggestions | 4 | 4
Meetings | 3 | 6
Meeting 13 | 3 | 3
Week 10 status meeting | 3 | 3
27-07-21 - 02-08-21 | 4.75 | 21
Website Enhancements | 5.8 | 18
Landing Page Development | 6 | 4
Settings Page Development | 6 | 2
Email verified Page Development | 3 | 2
Hosting the website | 8 | 3
Testing with Georgian students |  | 7
Meetings | 3 | 3
Meeting 14 | 3 | 3
03-08-21 - 09-08-21 | 3 | 14
Website Enhancements |  | 8
Bug-fixes |  | 8
Meetings | 3 | 6
Week 12 status meeting | 3 | 3
Meeting 15 | 3 | 3
Grand Total | 4.6514 | 239

## Weekly Budgeted vs Actual
Row Labels | Average of Task Budgeted Hours | Total Hours
<11-05-21 | 3 | 3
11-05-21 - 17-05-21 | 8.3333 | 25
18-05-21 - 24-05-21 | 7 | 18
25-05-21 - 31-05-21 | 3.55 | 21
01-06-21 - 07-06-21 | 5.8 | 16
08-06-21 - 14-06-21 | 3.0385 | 18.5
15-06-21 - 21-06-21 | 2.625 | 16.5
22-06-21 - 28-06-21 | 3.25 | 12.5
29-06-21 - 05-07-21 | 6 | 20.5
06-07-21 - 12-07-21 | 4.6 | 21
13-07-21 - 19-07-21 | 5.75 | 24
20-07-21 - 26-07-21 | 5.4 | 26
27-07-21 - 02-08-21 | 4.75 | 21
03-08-21 - 09-08-21 | 3 | 14
Grand Total | 4.6514 | 257

## Overall Budget vs Actual Data
Deliverable.Title | Budget Hours | Hours | Budget Cost | Actual Cost | Cost Variance
Project Workspace Set up | 20 | 6 | 1000 | 300 | 700
Database | 20 | 17 | 1000 | 850 | 150
Website Enhancements | 20 | 142 | 1000 | 7100 | -6100
Meetings | 20 | 67 | 1000 | 3350 | -2350
| 20 | 18 | 1000 | 900 | 100

## Overall Budget vs Actual Chart
Row Labels | Sum of Actual Cost | Sum of Budget Cost
Project Workspace Set up | 300 | 1000
Database | 850 | 1000
Website Enhancements | 7100 | 1000
Meetings | 3350 | 1000
Grand Total | 11600 | 4000